## Effort Estimation (hidden)
Theme | EPIC | User Stories | Task | Point Value | ~ Effort in Man Days | Roles
DI Upgrade |  |  |  | 0 | 0 | .Net Developer
| Login | Authentication |  | 8 | 5 | .Net Developer
|  | SSO Inegration |  | 8 | 5 | .Net Developer
Authorization
|  | Passwod Management |  | 5 | 4 | .Net Developer
| Dashboard | Dashboard |  | 8 | 5 | .Net Developer
|  | Reports |  | 8 | 5 | .Net Developer
|  | Search |  | 8 | 5 | .Net Developer
|  | Report Export |  | 5 | 4 | .Net Developer
|  | Audit Logs |  | 13 | 10 | .Net Developer
| Maintenance | Approver List |  | 8 | 5 | .Net Developer
|  | Customer |  | 8 | 5 | .Net Developer
|  | Customer Group |  | 8 | 5 | .Net Developer
|  | Configuration |  | 8 | 5 | .Net Developer
|  | Commercial Unit |  | 8 | 5 | .Net Developer
|  | Invoice Footer |  | 5 | 4 | .Net Developer
|  | Location |  | 5 | 4 | .Net Developer
|  | Sales Group |  | 5 | 4 | .Net Developer
|  | Sales Office |  | 5 | 4 | .Net Developer
|  | Sales Org |  | 5 | 4 | .Net Developer
|  | Site Admin |  | 5 | 4 | .Net Developer
| Cloud Development | Setting up MS Defender |  | 8 | 5 | Azure Developer
|  | Setting up Azure Storage |  | 8 | 5 | Azure Developer
| UX | UI Design |  | 40 | 40 | UX Developer
|  | JS Development |  | 13 | 10 | UX Developer
| Testing | Unit Testing |  | 13 | 10 | .Net Developer
|  | SIT |  | 40 | 40 | Tester
|  | UAT |  | 13 | 10 | Tester
|  | PIV |  | 2 | 2 | Tester
| DB Development | DB Admin |  | 13 | 10 | Backend DBA
|  | DB Development |  | 13 | 10 | Backend Developer
|  | Azure Development |  | 13 | 10 | Azure DevOps Developer
| DevSecOps Pipeline | Create Project |  | 1 | 1 | Azure DevOps Developer
|  | Create Azure Dashbaords |  | 8 | 5 | Azure DevOps Developer
|  | Create Repo |  | 1 | 1 | Azure DevOps Developer
|  | Create Artifacts |  | 3 | 3 | Azure DevOps Developer
|  | Setup Pipeline |  | 8 | 5 | Azure DevOps Developer
|  | Security Test Plans |  | 8 | 5 | Azure DevOps Developer
| Project Management | Scrum Master/PM |  |  | 50 | Project Manager
|  | BA |  |  | 25 | Business Analyst
|  | Tech Lead / App Architect/SA |  |  | 60 | Technical Architect

## Resources and Effort
| Resources Required | [17 empty] | Effort
App Name | SDA | SA | PM | BA | Architect | Tech Lead | Dev1 | Dev2 | Mobile Lead | Mobile Dev | Test Lead | Test Engineer | DBA | DB Developer | UX | UI | Cloud Architect | DevOps Engineer | Man Hours | Man Days | Man Months
DI | ü | ü | ü | ü | ü | ü | ü | ü | ý | ý | ü | ü | ü | ü | ü | ü | ü | ü | 5520 | 690 | 34.5
Survey | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | 5936 | 742 | 37.1
CWT | ü | ü | ü | ü | ü | ü | ü | ü | ý | ý | ü | ü | ü | ü | ü | ü | ü | ü | 4976 | 622 | 31
CAF | ü | ü | ü | ü | ü | ü | ü | ü | ý | ý | ü | ü | ü | ü | ü | ü | ü | ü | 12400 | 1550 | 78
R&I | ý | ý | ü | ü | ý | ü | ü | ý | ý | ý | ý | ü | ý | ý | ý | ý | ý | ý | 680 | 85 | 3.4
BBS | ý | ý | ü | ü | ý | ü | ü | ü | ý | ý | ý | ü | ý | ý | ý | ý | ý | ý | 992.0625 | 90.125 | 4.9603
Cadence | ý | ý | ü | ü | ý | ü | ü | ý | ý | ý | ý | ü | ý | ý | ý | ý | ý | ý | 1208 | 151 | 6.04
App Name | Man Hours | Man Days | Man Months
DI | 5520 | 690 | 34.5
Survey | 5936 | 742 | 37.1
CWT | 4976 | 622 | 31
CAF | 12400 | 1550 | 78
R&I | 921 | 115.125 | 5.7562
BBS | 1647 | 205.875 | 10.2938
Cadence | 2728 | 341 | 17.05
Totals | 34128 | 4266 | 213.7

## Complexity Summary
App Name | User Stories | Tasks | Sub Tasks | Web Forms
Digitalised Invoice (DI) | 36 | 60 | 8 | 82
Survey App (+Mobile) | 16 | 82 | 44 | 35
Credit Application Form (CAF) | 24 | 95 | 125 | 120
Certificate of Withholding Tax (CWT) | 13 | 49 | 5 | 22
BBS | 24 | 90 | 68 | 37
Cadence | 15 | 27 | 18 | 23
Risk & Insurance | 5 | 22 | 10 | 13

## All apps Estimation Summary
CCBPI Modernization Estimation | Digitalised Invoice (DI) |  |  | Survey App (+Mobile) |  |  | Credit Application Form (CAF) |  |  | Certificate of Withholding Tax (CWT) |  |  | Risk & Insurance Portal |  |  | Cadence |  |  | BBS
Roles | Effort In Hours | Effotrt In Days | Effort In Months | Effort In Hours | Effotrt In Days | Effort In Months | Effort In Hours | Effotrt In Days | Effort In Months | Effort In Hours | Effotrt In Days | Effort In Months | Effort In Hours | Effotrt In Days | Effort In Months | Effort In Hours | Effotrt In Days | Effort In Months | Effort In Hours | Effotrt In Days | Effort In Months
SDA | 56 | 7 | 0.35 | 56 | 7 | 0.35 | 120 | 15 | 0.75 | 56 | 7 | 0.35
SA | 56 | 7 | 0.35 | 56 | 7 | 0.35 | 120 | 15 | 0.75 | 56 | 7 | 0.35
PM | 272 | 34 | 2 | 336 | 42 | 2 | 712 | 89 | 4 | 256 | 32 | 2 | 111 | 13.875 | 0.69375 | 183 | 22.875 | 1.1438 | 253 | 31.625 | 1.5813
BA | 272 | 34 | 2 | 344 | 43 | 2 | 712 | 89 | 4 | 256 | 32 | 2 | 69 | 8.625 | 0.43125 | 195 | 24.375 | 1.2188 | 255 | 31.875 | 1.5938
Architect | 256 | 32 | 2 | 344 | 43 | 2 | 720 | 90 | 5 | 296 | 37 | 2
Tech Lead | 440 | 55 | 3 | 448 | 56 | 3 | 1120 | 140 | 7 | 408 | 51 | 3
Dev1 | 720 | 90 | 5 | 768 | 96 | 5 | 1704 | 213 | 11 | 648 | 81 | 4 | 660 | 82.5 | 4.125 | 1020 | 127.5 | 6.375 | 1860 | 232.5 | 11.625
Dev2 | 720 | 90 | 5 | 768 | 96 | 5 | 1704 | 213 | 11 | 648 | 81 | 4
Test Lead | 352 | 44 | 2 | 352 | 44 | 2 | 752 | 94 | 5 | 312 | 39 | 2
Test Engineer | 536 | 67 | 3 | 600 | 75 | 4 | 1328 | 166 | 8 | 520 | 65 | 3 | 81 | 10.125 | 0.50625 | 249 | 31.125 | 1.5562 | 360 | 45 | 2.25
DBA | 248 | 31 | 2 | 248 | 31 | 2 | 632 | 79 | 4 | 208 | 26 | 1
DB Developer | 432 | 54 | 3 | 456 | 57 | 3 | 1024 | 128 | 6 | 408 | 51 | 3
UX | 432 | 54 | 3 | 424 | 53 | 3 | 768 | 96 | 5 | 288 | 36 | 2
UI | 520 | 65 | 3 | 528 | 66 | 3 | 904 | 113 | 6 | 408 | 51 | 3
Cloud Architect | 160 | 20 | 1 | 160 | 20 | 1 | 160 | 20 | 1 | 160 | 20 | 1
DevOps Engineer | 160 | 20 | 1 | 160 | 20 | 1 | 160 | 20 | 1 | 160 | 20 | 1
Totals | 5520 | 690 | 37 | 5936 | 742 | 37.1 | 12400 | 1550 | 78 | 4976 | 622 | 33 | 921 | 115.125 | 5.7562 | 1647 | 205.875 | 10.2938 | 2728 | 341 | 17.05
User Stories | 36 |  |  | 16 |  |  | 24 |  |  | 13 |  |  | 5 | 5 | 5 | 15 | 15 | 15 | 24
Tasks | 60 |  |  | 82 |  |  | 95 |  |  | 49 |  |  | 22 | 22 | 22 | 27 | 27 | 27 | 90
Sub Tasks | 8 |  |  | 44 |  |  | 125 |  |  | 5 |  |  | 10 | 10 | 10 | 18 | 18 | 18 | 68
Web Forms | 82 |  |  | 54 |  |  | 120 |  |  | 22 |  |  | 13 | 13 | 13 | 23 | 23 | 23 | 37

## Summary_old (hidden)
APP | PM | BA | Architect | Tech Lead | Dev1 | Dev2 | Test Lead | Test Engineer | DBA | DB Developer | UX | UI | Cloud Architect | DevOps Engineer | App Effort (In Days | Months | Hours
Digitalised Invoice | 34 | 34 | 32 | 55 | 90 | 90 | 44 | 67 | 31 | 54 | 54 | 65 | 20 | 20 | 690 | 31.3636 | 5520
Survey Application | 42 | 43 | 43 | 56 | 96 | 96 | 44 | 75 | 31 | 57 | 53 | 66 | 20 | 20 | 742 | 33.7273 | 5936
CWT | 32 | 32 | 37 | 51 | 81 | 81 | 39 | 65 | 26 | 51 | 36 | 51 | 20 | 20 | 622 | 28.2727 | 4976
CAF | 89 | 89 | 90 | 140 | 213 | 213 | 94 | 166 | 79 | 128 | 96 | 113 | 20 | 20 | 1550 | 70.4545 | 12400
Total | 197 | 198 | 202 | 302 | 480 | 480 | 221 | 373 | 167 | 290 | 239 | 295 | 80 | 80 | 3604 | 163.8182 | 28832
Exact Month | 9.85 | 9.9 | 10.1 | 15.1 | 24 | 24 | 11.05 | 18.65 | 8.35 | 14.5 | 11.95 | 14.75 | 4 | 4 | 180.2
Rounded - Head Count | 2 | 2 | 2 | 3 | 4 | 4 | 2 | 3 | 1 | 3 | 2 | 3 | 1 | 1
CAF Values | 89 | 89 | 90 | 140 | 213 | 213 | 94 | 166 | 79 | 128 | 96 | 113 | 20 | 20

## Power Apps Estimation
Risk & Insurance Portal | Access Creation & Initiation | Requirements Gathering, User Story Creation, Sprint Backlogs, Acceptance Criteria | Build & Test (Web & Mobile Applications) | [8 empty] | Reworks & UAT | Go live & Hypercare | Total Effort
| Month 1 - June |  |  |  | Month 2 - July |  |  |  | Month 3 - August
| Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  |  | 921
Weeks | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
Developers |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
Efforts | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 30 | 30 | 660
QA |  |  |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
Effort | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 81
BA | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3
Effort | 9 | 9 | 9 | 9 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 9 | 69
PM | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1
Effort | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 3 | 111
Cadence | Access Creation & Initiation | Requirements Gathering, User Story Creation, Sprint Backlogs, Acceptance Criteria | Build & Test (Web & Mobile Applications) | [8 empty] | Reworks & UAT | Go live & Hypercare | Total Effort
| Month 1 - June |  |  |  | Month 2 - July |  |  |  | Month 3 - August
| Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  |  | 1647
Weeks | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
Developers |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1
Efforts | 0 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 30 | 1020
QA |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.3
Effort | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 9 | 249
BA | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Effort | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 195
PM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.1
Effort | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 3 | 183
BBS | Access Creation & Initiation | Requirements Gathering, User Story Creation, Sprint Backlogs, Acceptance Criteria | Build & Test (Web & Mobile Applications) | [8 empty] | Reworks & UAT |  |  |  |  | Go live & Hypercare | Total Effort
| Month 1 - June |  |  |  | Month 2 - July |  |  |  | Month 3 - August |  |  |  | Month 4 - September
| Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  |  | 2727
Weeks | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17
Developers |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
Efforts | 0 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 60 | 1860
QA |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.3
Effort | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 9 | 369
BA | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Effort | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 255
PM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.1
Effort | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 3 | 243
Since in Power Apps, developers will not be able to publish at the same time, hence the developers needs to be considered in different time zones or working hours, with overlapping hours
The timeline and estimation is entirely based on the captured features. Any change in the Scope will have to change the timeline.

## Resource Loading
Head Count | Role | Monthly Loading | Hourly Loading | FNT 1 | FNT 2 | FNT 3 | FNT 4 | FNT 5 | FNT 6 | FNT 7 | FNT 8 | FNT 9 | FNT 10 | FNT 11 | FNT 12 | FNT 13 | FNT 14 | FNT 15 | FNT 16 | FNT 17 | FNT 18 | FNT 19 | FNT 20
0.66667 | Project Manager | 9 | 5.33
1 | Senior BA | 8 | 8
1 | Presales Solution Architect | 3 | 6
1 | Senior Delivery Manager | 2 | 5.33
0.66667 | Technical Architect | 9 | 5.33
1 | .Net Technical Lead | 8 | 8
1 | Front End Technical Lead | 8 | 8
2 | Senior .Net Developer | 9 | 16
1 | Junior .Net Developer | 9 | 8
0.25 | Database Admin / Architect | 7 | 2
1 | SQL Developer | 7 | 8
1 | Senior SQL Developer | 7 | 8
1 | Senior UX Designer | 8 | 8
1 | Front End Developer | 7 | 8
2 | Senior Front end Developer | 8 | 8
1 | Senior UI Designer | 8 | 8
1 | Azure Cloud Architect | 3 | 5
1 | Senior Devops Engineer | 6 | 8
1 | Test Lead | 7 | 8
1 | Jr Test Engineer | 7 | 8
1 | Senior Test Engineer | 7 | 8
1 | Senior Mobile Developer | 6 | 8

## BBS
From Name | EPIC | User Story | Task | Sub Task | PM | BA | Architect | Tech Lead | Dev1 | Dev2 | QA Tester | Test Engineer | DBA | DB Developer | UX | UI
1. Behavior Based Safety Application
| 35+ | New Site | Create Site |  | 1 | 1 |  | 1 | 1 | 1
|  |  | Create Groups and Permissions | [5 empty] | 1 | 1
|  |  | Create Table structure to map all the tables | [5 empty] | 6 | 6
|  |  | Create Lists in Sharepoint | [5 empty] | 4 | 4
|  |  | Create Views for the list | [5 empty] | 2 | 2
PowerApps
Login Screen |  | Login Screen | Create New Screen with login Button. |  | 1 | 1 |  | 1 | 3 | 3 | 3
Dashborad |  | Dashborad | Create new sceen with UI Navigation |  | 1 | 1 |  | 1 | 1 | 1 | 3
|  |  | MU Coke BBS Compliance per site bar graph | Power BI Report |  |  |  |  | 5 | 5
|  |  | MU Average BBS Compliance per Calendar Period line graph. | Power BI Report |  |  |  |  | 5 | 5
|  |  | Banner with Notification message showing the pending Approvals | [5 empty] | 2.5 | 2.5
|  |  | Search and Filters | [5 empty] | 2 | 2
RCA Home |  | RCA Home | Create new sceen with UI Navigation (Header,home,Back,Menu) |  | 1 | 1 |  | 1 | 2 | 2 | 3
|  |  | Display all the Root Cause Analysis submitted for Approval | [5 empty] | 1 | 2
|  |  | RCA displays table of Date Period, Plant, perfomed by, Location, Status and action | [5 empty] | 2 | 2
|  |  | Sorting functions for each soloumns | [5 empty] | 1.5 | 1.5
Perform RCA |  | Perform RCA | Create new sceen with UI Navigation (Header,home,Back,Menu) |  | 1 | 1 |  | 1 | 2 | 2 | 3
|  |  | View RCA details | [5 empty] | 2 | 2
|  |  | Approve/ Reject buttons | By clicking on approve an Approve Confirmation pop up message will appear. Click Approve to proceed or click Cancel and close icon will dismiss the current screen display. |  |  |  |  | 2 | 2
|  |  | Display Notification on Approve/reject | If RCA submitted was approved “RCA submitted successfully approved.” and if rejwected “RCA submitted successfully Rejected" |  |  |  |  | 1.5 | 1.5
|  | Reports | Contains all reports for below modules.
Observation Report |  |  | Observation Report | Create new sceen with UI Navigation (Header,home,Back,Menu)Display Table listing details of Region, Sites, Observers, Date Observed, Area Observed, Task Observed. Each column listing can be sorted using the sorting icon beside each table column title Filter search and clear function Export report Icon | 1 | 1 |  | 1 | 8 | 8 | 2
RCA Report |  |  | RCA Report | Create new sceen with UI Navigation (Header,home,Back,Menu) ,Display Table listing details ofof Date Period, Site, Performed by, location and Status. Each column listing can be sorted using the sorting icon beside each table column title Filter search and clear function Export report Icon | 1 | 1 |  | 1 | 8 | 8 | 2
Effectiveness Report |  |  | Effectiveness Report | Create new sceen with UI Navigation (Header,home,Back,Menu), Display Table listing details of Period, Sites, Region, Critical Behaviour, Target Number of Answers, Actual Number of Answers, YES/NO/NA count, % Safe Behaviour and % Unsafe Behaviour. Each column listing can be sorted using the sorting icon beside each table column title Filter search and clear function Export report Icon | 1 | 1 |  | 1 | 8 | 8 | 2
Observation Compliance Report |  |  | Observation Compliance Report | Create new sceen with UI Navigation (Header,home,Back,Menu), Display Table listing details of Period, Site, Region, Critical Behavior, Target Number of Answers, Actual Number of Answers, YES/NO/NA count, % Safe Behavior and % Unsafe Behavior. Each column listing can be sorted using the sorting icon beside each table column title. Filter search and clear function Export report Icon | 1 | 1 |  | 1 | 8 | 8 | 2
BBS Compliance Report |  |  | BBS Compliance Report | Create new sceen with UI Navigation (Header,home,Back,Menu),Display Table listing details of Region, Plant, Period, Observation Compliance, % Observation, Unsafe Behavior, % Reduction, % Effectiveness, BBS Compliance for the Period and YTD BBS Compliance. Each column listing can be sorted using the sorting icon beside each table column title Filter search and clear function Export report Icon | 1 | 1 |  | 1 | 8 | 8 | 2
Admin Screen |  | Admin Site-Maintaince | Admin Site contains below sub-tab | [5 empty] | 3 | 3 | 1.5
Questions |  |  | Questions | Create new sceen with UI Navigation (Header,home,Back,Menu) ,Display List of Questions Edit/Deactive question Add new question | 1 | 1 |  | 1 | 4 | 4 | 1.5
445 Calendar |  |  | 445 Calendar | Create new sceen with UI Navigation (Header,home,Back,Menu), Display List Year, Period, Week, Start Date, and End date. Table be filtered by period and sorted per column. Download/Upload button to Download/Upload calendar | 1 | 1 |  | 1 | 4 | 4 | 2
Target Definition |  |  | Target Definition | Create new sceen with UI Navigation (Header,home,Back,Menu), displays Year, National BBS Compliance Target (%), Weekly Observation Target per user, Weekly Observation Target effectivity date and Action. Table be filtered by period and sorted per column. Add New Target, Edit target | 1 | 1 |  | 1 | 5 | 5 | 2
User Maintenance |  | (Can be done for roles is sharepoint) | User Maintenance | Create new sceen with UI Navigation (Header,home,Back,Menu), Table listing displays Name, Email Address, Site, User Role, Date Added, Last Access, Active and Action. Filter and sort by columns. Add New User, edit/delete user role. Activate or deactivate users. | 1 | 1 |  | 1 | 5 | 5 | 2
User Activation History |  | (Can be done for roles is sharepoint) | User Activation History | Table listing displays User, Is Active Status, Site, User Role, Created Date, Date Added. Sort and filter by columns. Edit history | 1 | 1 |  | 1 | 4 | 4 | 2
Unit Maintenance |  |  | Unit Maintenance | Create new sceen with UI Navigation (Header,home,Back,Menu), Table listing displays Name of Unit, Date Added, Active Status and Action. Filter and search. Add new Unit, Edit unit | 1 | 1 |  | 1 | 5 | 5 | 2
Unit Detail Maintenance |  |  | Unit Detail Maintenance | Create new sceen with UI Navigation (Header,home,Back,Menu), 3 sub Units-Commercial unit, Logistic unit and Manufacturing Unit. For each unit Filter and search. Add new Unit, Edit unit | 1 | 1 |  | 1 | 5 | 5 | 2
| Power Automate flows | Email Notification | Create a power automate flow for email notifications | [5 empty] | 4 | 4 | 2
|  | Export to excel | create power automate flow to export the gallery etails | [5 empty] | 4 | 4 | 2
2. Driver - Behavior Based Safety Application
| Sharepoint | New Site | Create Site |  | 1 | 1 |  | 1 | 1 | 1
|  |  | Create Groups and Permissions | [5 empty] | 1 | 1
|  |  | Create Table structure to map all the tables | [5 empty] | 6 | 6
|  |  | Create Lists in Sharepoint | [5 empty] | 4 | 4
|  |  | Create Views for the list | [5 empty] | 2 | 2
Dashboard screen | PowerApps | Dashboard | Create new sceen with UI Navigation |  | 1 | 1 |  | 1 | 2 | 2 | 2.5
|  |  | Submission per site bar graph | Power BI Report |  |  |  |  | 4.5 | 4.5
|  |  | Search and Filters | [5 empty] | 1.5 | 1.5
|  |  | Banner with Notification message | [5 empty] | 2 | 2
Reports Home |  | Reports Tab | Create new Screen UI for three categories (Observations, Effectiveness and Observation Compliance) |  | 1 | 1 |  | 1 | 3 | 3 | 2
|  |  | Create search and filters | [5 empty] | 1 | 1 | 1
Observation Report |  |  | Observation Report | Create a New UI navigation gallery in Reports Screen | 1 | 1 |  | 1 | 3 | 3
|  |  |  | Create a button to download excel of the current report which is displayed in the gallery |  |  |  |  | 2 | 2
|  |  |  | The gallery contains following columns (Region, Site, Reviewer, Date Reviewed and Driver) |  |  |  |  | 3 | 3
Effectiveness Report |  |  | Effectiveness Report | Create a New UI navigation gallery in Reports Screen | 1 | 1 |  | 1 | 3 | 3 | 2
|  |  |  | Create a button to download excel of the current report which is displayed in the gallery |  |  |  |  | 2 | 2
|  |  |  | The gallery contains following columns (Period, Site, Region, Critical Behavior, Target Number of Answers, Actual Number of Answers, YES/NO/NA count, % Safe Behavior and % Unsafe Behavior) |  |  |  |  | 3 | 3 | 2
Observation Compliance Report |  |  | Observation Compliance Report | Create a New UI navigation gallery in Reports Screen | 1 | 1 |  | 1 | 3 | 3 | 2
|  |  |  | Create a button to download excel of the current report which is displayed in the gallery |  |  |  |  | 2 | 2
|  |  |  | The gallery contains following columns (Period, Site, Region, Reviewer Name, Target Compliance, Observation Compliance, Target Number of Answers, Actual Number of Answers, YES/NO/NA count, % Safe Behavior and % Unsafe Behavior. ) |  |  |  |  | 4 | 4
Admin Screen |  | Admin Site | Create a dropdown menu containing(Admin site,Questions,Driver and Target Definition) |  | 1 | 1 |  | 1 | 3 | 3 | 2
Question Option |  |  | Question Option | Create New navigation And UI with a Gallery |  |  |  |  | 3 | 3 | 2
|  |  |  | Create a Button to Add Questions |  |  |  |  | 1 | 1 | 2
|  |  |  | Create a Active Button and a Action button in the gallery |  |  |  |  | 1 | 1
|  |  |  | Create a Pop up onclick on of add question |  |  |  |  | 1 | 1
|  |  |  | Create a text box inside the popupand a save button to save the edited/new question |  |  |  |  | 1 | 1
Driver List |  |  | Driver List |  | 1 | 1 |  | 1 |  |  | 2.5
|  |  |  | Create a Button to Add Driver |  |  |  |  | 2 | 2
|  |  |  | Create a Active Button and a Action button in the gallery |  |  |  |  | 2 | 2
|  |  |  | Create a Pop up onclick on of add Driver |  |  |  |  | 2 | 2
|  |  |  | Create a text box for last name, first name, middle name, dropdown for region and dropdown for site and a save button to save the edited/new driver |  |  |  |  | 2 | 2
|  |  |  | Create a download driver template option whhere an excel will be downloaded containing the template |  |  |  |  | 2 | 2
|  |  |  | Create a Bulk upload button which will use the same template file as an input for bulk upload of Driver |  |  |  |  | 2 | 2
|  |  |  | Create a popup for this Bulk upload and create a attachment option to place the template file and Create a upload button |  |  |  |  | 2 | 2
Target Definition |  |  | Target Definition | Create New navigation And UI with a Gallery and a Add Target Button | 1 | 1 |  | 1 | 3 | 3 | 2.5
|  |  |  | Create Columns with name (Target definition listing displays Year, Period, Week, Punch Card Compliance Target (%), Weekly Observation Target per user, Week Start date, Week End Date and Action.) Action column will be the edit button inside gallery |  |  |  |  | 2 | 2
|  |  |  | Create a pop up on click of add target and create the same field inside the columns |  |  |  |  | 2 | 2
| Power Automate flows | Email Notification | Create a power automate flow for email notifications | [5 empty] | 7 | 7 | 1
|  | Export to excel | create power automate flow to export the gallery details | [5 empty] | 10 | 10 | 1
3. Safety Officer (GMP) Aplication
| Sharepoint | New Site | Create Site |  | 1 | 1 |  | 1 | 2 | 2
|  |  | Create Groups and Permissions | [5 empty] | 1 | 1
|  |  | Create Table structure to map all the tables | [5 empty] | 6 | 6
|  |  | Create Lists in Sharepoint | [5 empty] | 5 | 5
|  |  | Create Views for the list | [5 empty] | 1 | 1
Dashboard screen | Powerapps | Dashboard | Create a new UI screen and Navigation whch contains header columns as Main menu, Dashboard, Home, Observations, RCA, Reports,Admin site |  | 1 | 1 |  | 1 | 2 | 2 | 2
|  |  | Create a MU BBS Compliance per plant bar graph and MU Average BBS Compliance per calendar period line graph | Power BI | 1 | 1 |  | 1 | 5 | 5 | 2
|  |  | Create a BBS MU Compliance per calendar period that displays a line graph which shows BBS compliance score of specific assigned plant as of current period. |  | 1 | 1 |  | 1 | 3 | 3 | 2
Home screen |  | Home Screen | Create Home tab with new UI and navigation | Crate a banner with notifictaion message for safety officer, conduct Observation Button and recent observations table list columns: Observer name, Observation Date, Plant, Task Observed and Area Observed. | 1 | 1 |  | 1 | 3 | 3 | 2
|  |  |  | Add No items to show.” message display when no recent observations were added or available. |  |  |  |  | 2 | 2
Observations |  | Observations | Create New UI and Navigation with a Conduct Observation button |  | 1 | 1 |  | 1 | 3 | 3 | 4
|  |  | Create a shop checklist screen with new Navigation and UI | [5 empty] | 2 | 2
|  |  | Shop checklist screen should contain Observer name , date observed plant, task observed, area observed | [5 empty] | 2 | 2
|  |  | Create Yes/NO buttons for the following fields (Using appropriate tools, Always "Eyes on path", Safe position and location, Rightway of lifting, Following SOPs, Always 3 point contact, test, new test questions | [5 empty] | 2 | 2
|  |  | Create a commendation field in text box given below the form | [5 empty] | 1 | 1
|  |  | Create a Coaching provided field in text box | [5 empty] | 1 | 1
|  |  | Create a Unsafe Condition Note field in text box | [5 empty] | 2 | 2
|  |  | Create a submit buton to submit the checklist | [5 empty] | 1 | 1
RCA |  | RCA | Create new screen with UI Naviation |  | 1 | 1 |  | 1 | 2 | 2 | 3
|  |  | Gallery to display column date period, plant, performed by, location, status and action | [5 empty] | 3 | 3
|  |  | Sort function beside each coloumn name | [5 empty] | 3 | 3
|  |  | Edit RCA screen | [5 empty] | 3 | 3
|  |  | Save as draft option | [5 empty] | 3 | 3
|  |  | Create new RCA option | [5 empty] | 3 | 3
|  |  | Add button to add new action plan | [5 empty] | 2 | 2
|  |  | Acitvate/deactivate action plan | [5 empty] | 2 | 2
|  |  | Edit /delete action plan | [5 empty] | 3 | 3
|  |  | Pop up for confrimation | [5 empty] | 3 | 3
|  |  | Submit function | [5 empty] | 5 | 5
Reports |  | Reports | Reports Screen contains all reports tab available in the system such as Observations, RCA, Effectiveness, Observation Compliance and BBS Compliance. |  | 1 | 1 |  | 1 | 2 | 2 | 2
Observations Report |  |  | Observations Report | Create new UI navigation screen With Gallery which dispalys Region,Site Observer, Date Observed,Area Onserved and Task Observed | 1 | 1 |  | 1 | 3 | 3 | 5
|  |  |  | Sort and filter of each coloumn |  |  |  |  | 2 | 2
|  |  |  | Clear button o reset or clear filter |  |  |  |  | 2 | 2
|  |  |  | Button to export gallery details to excel report |  |  |  |  | 2 | 2
RCA Report |  |  | RCA Report | Create new UI navigation screen With Gallery which dispalys of Date Period, Plant, Performed By, Location and Status. | 1 | 1 |  | 1 | 3 | 3 | 5
|  |  |  | Sort and filter of each coloumn |  |  |  |  | 2 | 2
|  |  |  | Clear button o reset or clear filter |  |  |  |  | 2 | 2
|  |  |  | Button to export gallery details to excel report |  |  |  |  | 2 | 2
Effectiveess Report |  |  | Effectiveess Report | Create new UI navigation screen With Gallery which dispalys of Period, Plant, Region, Critical Behavior, Target Number of Answers, Actual Number of Answers, YES/NO/NA count, % Safe Behavior and % Unsafe Behavior | 1 | 1 |  | 1 | 4 | 4 | 5
|  |  |  | Sort and filter of each coloumn |  |  |  |  | 1 | 1
|  |  |  | Clear button o reset or clear filter |  |  |  |  | 1 | 1
|  |  |  | Button to export gallery details to excel report |  |  |  |  | 1 | 1
Observation Compliance Report |  |  | Observation Compliance Report | Create new UI navigation screen With Gallery which dispalys of Period, Site, Region, Critical Behavior, Target Number of Answers, Actual Number of Answers, YES/NO/NA count, % Safe Behavior and % Unsafe Behavior. | 1 | 1 |  | 1 | 4 | 4 | 5
|  |  |  | Sort and filter of each coloumn |  |  |  |  | 2 | 2
|  |  |  | Clear button o reset or clear filter |  |  |  |  | 1 | 1
|  |  |  | Button to export gallery details to excel report |  |  |  |  | 1 | 1
BS Compliance Report |  |  | BS Compliance Report | displays table with details of Region, Plant, Period, Observation Compliance, % Observation, Unsafe Behavior, % Reduction, % Effectiveness, BBS Compliance for the Period and YTD BBS Compliance. | 1 | 1 |  | 1 | 5 | 5 | 5
|  |  |  | Filter and search |  |  |  |  | 2 | 2
|  |  |  | Button to export to excel report |  |  |  |  | 2 | 2
|  |  |  | Clear button o reset or clear filter |  |  |  |  | 2 | 2
Admin screen |  | Admin Site | User Maintainace | Create New Ui navigation screen | 1 | 1 |  | 1 | 6 | 6 | 5
|  |  |  | Gallery to show user name , emai, role. date added, last access, etc |  |  |  |  | 4 | 4
|  |  |  | Search and Sort filter |  |  |  |  | 2 | 2
|  |  |  | Toggle to active deactive user |  |  |  |  | 4 | 4
37 | 11 | 24 | 90 | 68 | 40 | 40 | 0 | 40 | 368.5 | 369.5 | 112.5
[9 empty] | 46.0625 | 46.1875 | 14.0625
|  | Hours (Dev1 + Dev 2) | Days
| Total Development hours | 738 | 46.0625
| Total Testing Hours | 14.0625 | 14.0625
| Requirement Gathering Hours | 64 | 8
| Data Migration | 48 | 6
| UAT | 128 | 16
Go live
|  | 992.0625 | 90.125

## Cadence
Form Name | EPIC | User Story | Task | Sub Task | PM | BA | Architect | Tech Lead | Dev in days | Dev2 | Test Lead | QA Tester | DBA | DB Developer | UX | UI
Announcement | Mobile Application | Announcement | Announcement Details |  | 1 | 1 |  | 1 | 1 |  |  | 6
|  |  | Weekly Planner -Schedule sessions for the riders -Create a new session -Select drivers -Color coded for drivers for threshold criteria -Calendar view of all schedules | [5 empty] | 5
DSP Route Ride |  | DSP Route Ride | Dashboard -Date filters -Search -Dashboard reports of all outlets that answers yes to the survey -Click graph to show survey result for the outlets |  | 1 | 1 |  | 1 | 3 |  |  | 6
|  |  | Team Profile - DSP Rider information -Summary, Current Performance, Timeline | [5 empty] | 3
DSP Route Ride |  | Route Ride Session | Start session -DSP Attendance form -Outlets selection (Choice) - Action items (Yes/No) Session Summary -4 input fields Further Remarks Remarks Input fields (Opportunities, Next Steps, Remarks etc.) Signature (can be desinatory digital signature or signature using pen input) End Session |  | 1 | 1 |  | 1 | 5 |  |  | 5
|  |  | Summary -opportunities (Dynamic input fields) Current Performance -Training objectives etc. Timeline -Past activity -Audit logs like feature -Calendar view and click to view the activity | [5 empty] | 5
Dashboard |  | AAA+ Survey | Dashboard | 5 category reports (Available, Alam na meron, Ayos ang presyo, Dapat Malamig, Tottal AAA+ score) -Date filter -View Survey results | 1 | 1 |  | 1 | 5 |  |  | 6
Survey Form |  |  | Survey Form | Driver can only see this screen if they have a session scheduled -Display an info message Choose outlets and answer the form Form design is multiple input fields |  |  |  |  | 5
Survey Results |  |  | Survey Results | 2 Tab unsyn and sync AAA+ and Glass survey review Sync all survey/ Sync today |  |  |  |  | 3
Enroll Outlet |  | Outlet Enrollment | Enroll Outlet | Fill form to enroll and outlet | 1 | 1 |  | 1 | 3 |  |  | 5
Outlets |  |  | Outlets | Outlet results (sync, unsyn tab to view each) Unsyc may be edited |  |  |  |  | 3
AD Dashboard |  | AD Dashboard | Power BI | Need to understand if any modifications required or data can be directly connected | 1 | 1 |  | 1 | 5
Survey Questions | Web Application | AAA+/Glass survey | Survey Questions | Survey Forms Searching questions Add New -Name -Questions (ability to add) -Question forms (This is dynamic needs to check) preview Delete Status (currently as colored icons) Edit | 1 | 1 |  | 1 | 5 |  |  | 6
Survey Reasons |  |  | Survey Reasons | Add survey reasons Search *Similar to survey forms in functionality |  |  |  |  | 3
Survey Schedule |  |  | Survey Schedule | Add schedule -New schedule form -Criterias and rules on some fields Upload Schedule -As per the export excel file format Filters/search/reset etc. -Download functonality Export to excel functionality (Could be power automate connected to SP) |  |  |  |  | 3
Report |  |  | Report | Data dashboard similar to survey forms Export/Download to excel functionality Filters Views |  |  |  |  | 3
Survey Questions |  | Route Ride | Survey Questions | Similar to AAA survey questions All survey questions inputted here will be input in the AAA survey questions | 1 | 1 |  | 1 | 3 |  |  | 6
Route Ride Threshold criteria |  |  | Route Ride Threshold criteria | Configuration data Admin configurations for survey data criteria |  |  |  |  | 5
Objectives |  |  | Objectives | Objective data view Add new |  |  |  |  | 2
Route Ride Report |  |  | Route Ride Report | Data view of all route ride results Filters, search Export summary (From route ride dashboard) Export functionality |  |  |  |  | 3
Glass Survey |  | Glass Survey | Survey Questions | Survey Forms Searching questions Add new preview Delete Status (currently as colored icons) Edit | 1 | 1 |  | 1 | 3 |  |  | 6
Report |  |  | Report | Data dashboard similar to survey forms Export/Download to excel functionality Filters Views |  |  |  |  | 3
Survey Frequency |  | Survey Frequency | Data view to view next visit for AAA and glass Filters Seach Reset |  | 1 | 1 |  | 1 | 3
DSP Attendance |  | DSP Attendance | Similar to Survey reports/questions with data view All reports from mobile app Export funcitonality |  | 1 | 1 |  | 1 | 3 |  |  | 4
Enrolled outlets |  | Enrolled outlets | Similar to DSP reports/questions with data view All reports from mobile app Export funcitonality |  | 1 | 1 |  | 1 | 3 |  |  | 4
User Maintenance |  | User Maintenance | Announcements | Data view Add announcements -Form to add new -Image upload Upload Edit Delete Export Filters/Search etc. Download template (This can be done backend) | 1 | 1 |  | 1 | 3 |  |  | 6
|  |  | Survey Limit | Data View Create New -Form to add new |  |  |  | 1 | 3
|  | Email Notifications | [5 empty] | 1 | 2 |  |  | 4
|  | DB Configuration | [5 empty] | 1 | 5
23 | 2 | 15 | 27 | 18 | 13 | 13 | 0 | 16 | 101 | 0 | 0 | 64 | 0 | 0 | 0 | 0
Days
| Total Development hours | 808 | 101
| Total Testing Hours | 256 | 32
| Requirement Gathering Hours | 40 | 5
| Data Migration | 40 | 5
| UAT | 64 | 8
Go live
1208

## Risk & Insurance
From Name | EPIC | User Story | Task | Sub Task | PM | BA | Architect | Tech Lead | DEV (Hours) | QA Tester | DBA | DB Developer | UX | UI
Mock Up Screens
| PowerApps | Prepare Mockup Screens | Create the Mockup Screens for all features |  | 1 | 1 |  | 1 | 30
| Sharepoint | Sharepoint Site creation- Backend | Create Site |  | 1 | 1 |  | 1 | 1
|  |  | Create Groups and Permissions | [5 empty] | 1
|  |  | Create Table structure to map all the tables | [5 empty] | 12
|  |  | Create Lists in Sharepoint | [5 empty] | 12
|  |  | Create Views for the list | [5 empty] | 6
Login | PowerApps | Login Screen | Create New Screen for to Login as Roles | Banner, login button | 1 | 1 |  | 1 | 15 | 4
|  |  | Bug fixig | [5 empty] | 3
Admin Home |  | Admin Home Screen | Create New screen with UI Navigations |  | 1 | 1 |  | 1 | 5 | 5
|  |  | Create Gallery to show the Master List of Vechiles details | [5 empty] | 15
|  |  | Create Search and Sorting Function based of Insurance type | [5 empty] | 6
|  |  | Bug fixig | [5 empty] | 5
|  | Maintenance Modules | Create New Screen to Add/Update Below Modules |  | 1 | 1 |  | 1 | 8
Users |  |  | Users | users (Requestor,Broker,Claim Approver, Loa Approver) can be created, this consists of search by filter, reset and action which includes edit and delete. |  |  |  |  | 24 | 6
|  |  |  | Testing and Bug fixig |  |  |  |  | 5
Claims |  |  | Claims Documents | Search, filter, to create new documnet type. |  |  |  |  | 18 | 6
|  |  |  | Testing and Bug fixig |  |  |  |  | 4
Service Centers |  |  | Service centers | search, reset and to create new service center which also includes the action of edit and delete |  |  |  |  | 18 | 6
|  |  |  | Testing and Bug fixig |  |  |  |  | 4
Adjusters |  |  | Adjusters | Actions including edit, delete and create new adjusters. Search and filter |  |  |  |  | 18 | 6
|  |  |  | Testing and Bug fixig |  |  |  |  | 4
Regions |  |  | Regions | Add new ,delete,Edit Regions. Search and filter fuction |  |  |  |  | 18 | 6
|  |  |  | Testing and Bug fixig |  |  |  |  | 4
Plants |  |  | Plants | Add new ,delete, Edit Plants. Search and filter fuction |  |  |  |  | 18 | 6
|  |  |  | Testing and Bug fixig |  |  |  |  | 4
Vechile Types |  |  | Vehicle types | Add new, delete, Edit Vechile type. Search and filter fuction |  |  |  |  | 18 | 6
|  |  |  | Testing and Bug fixig |  |  |  |  | 4
Asset Class |  |  | Asset class | Add new, delete, Edit Asset class. Search and filter fuction |  |  |  |  | 18 | 6
|  |  |  | Testing and Bug fixig |  |  |  |  | 4
|  | Requestor Screen | Gallery list to show cliams submitted |  | 1 | 1 |  | 1 | 14 | 8
|  |  | Create Search for claims based on data range | [5 empty] | 4
|  |  | Button to create a claim | [5 empty] | 3
|  |  | Create form - Includes Motor vehicle, Claim type and Documents | [5 empty] | 6 | 3
|  |  | Submit function to save the details | [5 empty] | 3
|  |  | Bug fixig | [5 empty] | 8
Claims Documents |  | View Screen | View the claim form |  | 1 | 1 |  | 1 | 14 | 6
|  |  | Can edit/upload document | [5 empty] | 4
|  |  | Submit function to save the details | [5 empty] | 6
|  |  | Bug fixig | [5 empty] | 5
|  | Approver | View the claim form |  | 1 | 1 |  | 1 | 6 | 5
|  |  | Approve /Reject button with popup | [5 empty] | 4
|  |  | Bug fixig | [5 empty] | 5
Dashboard | PowerBI | Dashborad Screen | To display chart of settled claim and outstanding claim |  | 1 | 1 |  | 1 | 16 | 6
|  |  | Bug fixig | [5 empty] | 2
| Power Automate Flow | Email Notification flows | Email Notifiation on submission of claim request |  | 1 | 1 |  | 1 | 5 | 3
|  |  | Email notification on Appove rejects actions | [5 empty] | 5 | 2
|  |  | Email flow to extract file from sftp folder | Motor vehicles (vehicles are managed), where they get data synced with SAP via SFTP and can edit the details. Two files are extracted which includes Asset and Equipment where Asset consists of identification number (asset number) and Equipment consists of vehicle information. |  |  |  |  | 20 | 6
13 | 2 | 5 | 22 | 10
| Total Hours |  |  |  | 10 | 10 |  | 10 | 432 | 96 | 0 | 0 | 0 | 0
|  |  | Hours | Days |  |  |  | Total dev Days | 54 | 12
|  | Total Development hours | 432 | 54
|  | Total Testing Hours | 96 | 12
|  | Requirement Gathering Hours | 64 | 8 |  |  |  |  | 480 | 120
|  | Data Migration | 24 | 3
|  | UAT | 64 | 8
Go live
|  | Total hours/DAYS | 680 | 85

## CAF Effort
EPIC | User Story | Task | Sub Task | PM | BA | Architect | Tech Lead | Dev1 | Dev2 | Test Lead | Test Engineer | DBA | DB Developer | UX | UI
| Customer Login |  |  | 5 | 5 | 5 | 8 | 10 | 10 | 3 | 6 | 1 | 1 | 2 | 2
Get Link
Update Details
Verify and Login
Authorization
Forgot Password
Back to email
SSO Integration
| Admin Dashbaord |  |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 3 | 2 | 3
Menu
List View
Admin Portal
|  | Config Setup |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 3 | 2 | 4
|  | Admin User Setup |  | 2 | 2 | 2 | 3 | 5 | 5 | 1 | 3 | 1 | 3 | 2 | 3
Search
List View
Reset
Add Existing User
List view
Add all
Cancel
List View
Remove
|  | Role Details Setup |  | 2 | 2 | 2 | 3 | 5 | 5 | 1 | 3 | 1 | 3 | 2 | 3
Auto Create Role Setup
Save
Remove
List View
Route Code Email Setup
|  | General Trade |  | 2 | 2 | 2 | 3 | 5 | 5 | 1 | 3 | 1 | 3 | 2 | 3
List View
Select File & Import Data
Download Data
Setup Data
Save
|  | Modern Trade |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 3 | 2 | 3
List View
| Audit Logs |  |  | 3 | 3 | 3 | 4 | 8 | 8 | 3 | 5 | 3 | 5 | 3 | 5
List View
Audit Logs
Expand Details
Quick Logs
View
|  | Trigger Audit Log Time | Schedular
Internal Users/Intenal Roles
|  | Download All Users |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 2
List View
View Users
|  | Modern Trade |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1
List View
View Users
Add
Back
List View
Remove
|  | General Trade |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1
List View
View Users
Add
Back
List View
Remove
|  | Special |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1
List View
View Users
Add
Back
List View
Remove
| Approvers |  |  | 3 | 3 | 3 | 4 | 8 | 8 | 3 | 5 | 3 | 5 | 3 | 5
List View
Search
Reset
Select File
Upload File
Download Template
Download Records
Clear Records
Modern Trade
Trade
Finance
General Trade
Trade
Finance
| Approval Metrix |  |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 2
List View
|  | Credit Application |  | 5 | 5 | 5 | 7 | 12 | 12 | 3 | 5 | 5 | 8 | 6 | 9
Modern Trade
List View
Back
Add/Edit
Load Details
Actions
Remove
General Trade
List View
Back
Add/Edit
Load Details
Actions
Remove
|  | Updater Application |  | 5 | 5 | 5 | 7 | 12 | 12 | 3 | 5 | 5 | 4 | 4 | 5
Modern Trade
List View
Back
Add/Edit
Load Details
Actions
Remove
General Trade
List View
Back
Add/Edit
Load Details
Actions
Remove
|  | Reinstatement Application |  | 5 | 5 | 5 | 7 | 12 | 12 | 7 | 12 | 5 | 4 | 4 | 5
Modern Trade
List View
Back
Add/Edit
Load Details
Actions
Remove
General Trade
List View
Back
Add/Edit
Load Details
Actions
Remove
| Trade Sub Types |  |  | 2 | 2 | 2 | 3 | 4 | 4 | 2 | 3 | 2 | 3 | 2 | 3
List View
Search
Reset
Add New
Load Details
| File Types |  |  | 2 | 2 | 2 | 3 | 4 | 4 | 2 | 3 | 2 | 3 | 2
List View
Search
Reset
Add New
Load Details
| Business Reasons |  |  | 2 | 2 | 2 | 3 | 4 | 4 | 2 | 3 | 2 | 3 | 2
List View
Search
Reset
Add New /Edit
| Channel Types |  |  | 2 | 2 | 2 | 3 | 4 | 4 | 2 | 3 | 2 | 3 | 2
List View
Search
Reset
Add New/Edit
| Market Shares |  |  | 2 | 2 | 2 | 3 | 4 | 4 | 2 | 3 | 2 | 3 | 2
List View
Search
Reset
Add New/Edit
Business Requirements |  |  |  | 2 | 2 | 2 | 3 | 4 | 4 | 2 | 3 | 2 | 3 | 2 | 1
Select File
Download Records
Upload Files
General Trade
|  | Sole Proprietorship |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1
Search
Reset
List View
Add New
|  | Corporation |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1
Search
Reset
List View
Add New
|  | Corporative |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1
Search
Reset
List View
Add New
Modern Trade
|  | Sole Proprietorship |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1
Search
Reset
List View
Add New
|  | Corporation |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1
Search
Reset
List View
Add New
|  | Corporative |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1
Search
Reset
List View
Add New
| Reinstatement History |  |  | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 4 | 2 | 3
Select File
Import
Template
List View
Reports
|  | List View |  | 4 | 4 | 4 | 6 | 10 | 10 | 6 | 10 | 4 | 6 | 5 | 7
Search
Export to Excel
Generate Report
Credit Application
Updater Application
Reinstatement Application
| CAF Application - Customer |  |  | 5 | 5 | 5 | 10 | 20 | 20 | 7 | 12 | 5 | 8 | 10 | 10
List View
View CAF
New /Update Credit application
Back
Basic Information
References
Authorization
Upload Signature
View CAF
Audit Trail
| CAF Application - Approver |  |  | 10 | 10 | 10 | 15 | 25 | 25 | 15 | 25 | 5 | 8 | 10 | 10
Review/Endorsement
List View
Search
View CAF
Reinstatement Application
New Reinstatement Application
List View
Search
View CAF
Approver View
| Customer Management |  |  | 3 | 3 | 3 | 4 | 6 | 6 | 4 | 6 | 3 | 5 | 3 | 4
Select File for mass upload
Download all customers
Mass upload customers
Search
List View
Reset
|  | Add New |  | 3 | 3 | 3 | 5 | 7 | 7 | 4 | 6 | 3 | 6 | 3 | 4
Basic Requirementss
Reference and Requirements
Back
Next
Save
| Email Functionality |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
| Windows Schedular |  |  | 3 | 3 | 4 | 4 | 8 | 8 | 4 | 8 | 2 | 5 | 4 | 5
|  |  |  | 89 | 89 | 90 | 140 | 213 | 213 | 94 | 166 | 79 | 128 | 96 | 113
| 24 | 95 | 125

## CWT Effort
EPIC | User Story | Task | Sub Task | Web Forms | PM | BA | Architect | Tech Lead | Dev1 | Dev2 | Test Lead | Test Engineer | DBA | DB Developer | UX | UI
| Logo & Menu |  |  | Authentication & Authorization | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 2 | 3
|  | Login Lable |  | Reports
|  | Logo |  | Extract
|  | Logout |  | List View
|  | App Menu items |  | Certificates
| Login Feature |  |  | Preview | 2 | 2 | 3 | 4 | 6 | 6 | 2 | 3 | 1 | 2 | 2 | 3
|  | Login |  | List View
|  | Remember Me |  | Vendors
|  | Forgot Password |  | Bulk Upload
|  | Authorization |  | Add
|  | Logout |  | Import
| Certificates |  |  | Edit | 3 | 3 | 3 | 6 | 8 | 8 | 3 | 5 | 1 | 2 | 2 | 3
|  | Search |  | Maintenence
|  | Preview |  | Users List
|  | List View |  | Create User
|  | Download |  | Edit User
|  | Back |  | Audit Lots
| Vendors |  |  | CWT Changes | 3 | 3 | 4 | 6 | 9 | 9 | 3 | 6 | 2 | 5 | 3 | 5
|  | Search |  | Configuration
|  | List View |  | Tax Codes
|  | Create Vendor |  | Bulk Upload
|  | Exxtract Vendors |  | Create Tax Codes
Edit Vendor
Bulk Upload
Cancel
Maintainance
| Users |  |  |  | 2 | 2 | 3 | 4 | 6 | 6 | 4 | 6 | 3 | 5 | 3 | 4
Search
List View
Create User
Edit User
Delete User
Cancel
| Audit Logs |  |  |  | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 4 | 2 | 4 | 2 | 3
Search
List View
| CWT Changes |  |  |  | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 4 | 2 | 4 | 2 | 3
Search
List View
| Company Codes |  |  |  | 3 | 3 | 3 | 4 | 6 | 6 | 3 | 5 | 2 | 4 | 3 | 4
Search
List View
Create Company
Edit Company
Cancel
| Configuration |  |  |  | 4 | 4 | 4 | 6 | 10 | 10 | 6 | 8 | 4 | 7 | 5 | 7
SFTP Settings
Custom Calendar
CWT Custom Template
| Tax Codes |  |  |  | 2 | 2 | 3 | 4 | 6 | 6 | 4 | 6 | 3 | 5 | 3 | 4
Search
List View
Create Tax Code
Edit Tax Code
Upload From File
Cancel
| Reports |  |  |  | 3 | 3 | 3 | 4 | 6 | 6 | 3 | 5 | 2 | 4 | 3 | 4
Search
List View
Reset
Extract to Excel
| Email Functionality |  |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
| Windows Schedular |  |  |  | 3 | 3 | 4 | 4 | 8 | 8 | 4 | 8 | 2 | 5 | 4 | 5
| 13 | 49 | 0 | 22

## Digitalized Invoice Effort
Epic | User Story | Task | Sub Task | Web Forms | PM | BA | Architect | Tech Lead | Dev1 | Dev2 | Test Lead | Test Engineer | DBA | DB Developer | UX | UI | Cloud Architect | DevOps Engineer
Login Feature |  |  |  | Dashboard | [12 empty] | 20 | 20
| Login |  |  | Reports | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 2 | 2
| SSO |  |  | Audit Logs
| Authorization |  |  | Print Logs
| Password Change |  |  | Approver Logs
| Logout |  |  | Email Logs
Dashboard |  |  |  | Invoice Logs | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 2 | 3 | 3
| Total Count of Invoices |  |  | Maintenance
| Total amount due |  |  | Approver List
| total count of re-print |  |  | Add
| Total count of pending |  |  | Edit
| Search - Location filter |  |  | Bulk Add
| Search - Dare filter |  |  | Select
Report |  |  |  | Customer | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
| Filter Report |  |  | Add
| Export Report |  |  | Edit
| Report List View |  |  | Bulk Add
Select
Audit Logs |  |  |  | Customer Group | 4 | 4 | 0 | 8 | 12 | 12 | 8 | 12 | 4 | 8 | 8 | 8
| Print Log | Filter Search |  | Add
|  | Export Report |  | Edit
|  | List View |  | Bulk Add
| Approver Log | Filter Search |  | Select
|  | Export Report |  | Configuration
|  | List View |  | Commercial Unit
| Email Log | Filter Search |  | Add
|  | Export Report |  | Edit
|  | List View |  | Bulk Add
| Invoice Log | Filter Search |  | Select
|  | Export Report |  | Invoice Footer
|  | List View |  | Add
Maintainance |  |  |  | Edit | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 2 | 3 | 3 | 4
| Approver List |  |  | Bulk Add
|  | Search Filter |  | Select
|  | Approvers without location |  | Location
|  | List View |  | Add
|  | Bulk Upload |  | Edit
|  |  | Download Template | Bulk Add
|  |  | Upload file | Select
|  | Add Approver |  | Sales Group | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 2 | 3 | 3 | 4
|  |  | Personal Information | Add
|  |  | Additional Information | Edit
|  |  | User Status | Bulk Add
|  |  | Approver Type | Select
|  |  | Add Locarion | Sales Office
|  |  | List Location | Add
|  | Edit Approver |  | Edit | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1
Bulk Add
| Customer |  |  | Select | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 2 | 3 | 3 | 4
|  | Bulk Upload |  | Sales Org
|  | Add Customer |  | Add
|  | List View |  | Edit
|  | Activate |  | Bulk Add
|  | De-Activate |  | Select
| Customer Group |  |  | Site Admin | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 2
|  | Bulk upload |  | Add
|  | Add Customer Group |  | Edit
|  | Edit Customer |  | Bulk Add
| Configuration |  |  | Select | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 2
|  | Customer Group Entries UI |  | Authentication & Authorization
|  | Send Email |  | Send Notification
|  | Send SMS |  | Win Schedular
| Commercial Unit |  |  | Download Template | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 2
|  | Bulk upload |  | Upload file
|  | Add Unit |  | Personal Information
Additional Information
User Status
| Invoice Footer |  |  | Approver Type | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 2
|  | Add Invoice Footer |  | Add
|  | Edit Invoice Footer |  | Edit
|  | Filter Search |  | Bulk Add
|  | List View |  | Select
Add Locarion
| Location |  |  | Add | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 2 | 3 | 3 | 4
|  | Bulk Upload |  | Edit
|  | Add Location |  | Bulk Add
|  | Save Location |  | Select
|  | Cancel Location |  | List Location
|  | List View |  | Add
| Sales Group |  |  | Edit | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 2 | 3 | 3 | 4
|  | Bulk Upload |  | Bulk Add
|  | Add Sales Group |  | Select
Edit Sales Group
Cancel Sales Group
List View
| Sales Office |  |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 2 | 3 | 3 | 4
Bulk Upload
Add Sales Office
Edit Sales Office
Cancel Sales Office
List View
| Sales Org |  |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 2 | 3 | 3 | 4
Bulk Upload
Add Sales Org
Edit Sales Org
Cancel Sales Org
List View
| Site Admin |  |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 2 | 3 | 3 | 4
Add Site Admin
Edit Site Admin
Cancel Site Admin
List View
Add Location
| Email and SMS Functinality |  |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
| Windows Schedular |  |  |  | 3 | 3 | 4 | 4 | 8 | 8 | 4 | 8 | 2 | 5 | 4 | 5
5 | 31 | 60 | 8 | 82 | 34 | 34 | 32 | 55 | 90 | 90 | 44 | 67 | 31 | 54 | 54 | 65 | 20 | 20

## Survey App Details (hidden)
EPIC | User Story | Task | Sub Task | PM | BA | Architect | Tech Lead | Dev1 | Dev2 | Test Lead | Test Engineer | DBA | DB Developer | UX | UI | Cloud Architect | DevOps Engineer
Login features
Login
Forgot password
Remember Me
Logout
Authorization
Side Pane
|  | Account settings | User details
Change password
Menu
Users
Manage users
Search
Reset
Export
List view
Add user
|  | Add multiple user | Download user template
Download user assignment template
upload file
Edit user
Cancel & Back
User assignment
Department
Search
Export
List view
Add Department
Edit Department
Customer group
Search
Export
List view
Add customer group
|  | Add multiple customer group | Download template
Upload file
Cancel & Back
Edit customer group
Territory
Search
Export
List view
Add Territory
Edit Territory
Commericial unit
Search
Export
List view
Add commercial unit
|  | Add multiple commercial unit | Download template
Upload file
Cancel & Back
Edit commercial unit
Region
Search
Export
List view
Add region
|  | Add multiple region | Download region template
Download commericial unit template
Download territory data template
Upload file
Cancel & Back
Edit commercial unit
Sales location
Search
Export
List view
Add sales location
|  | Add multiple sales location | Download sales location template
Download region template
Upload file
Cancel & Back
Edit sales location
Surveys
Survey List View
Dashboard
Total Survey
Published
Draft
Expired
Closed
Actions
Duplicate Report
Download Export Report
Close Survey
View Respondents
| Surveys |  | Preview Survey
Search
|  | Create Survey | Question display
Add section
|  | Add Question | Select type of question
Edit question
Delete question
Change question type
Move to section
|  | Edit Survey | Question display
Add section
|  | Add Question | Select type of question
Edit question
Delete question
Change question type
Move to section
Duplicate survey
Close survey
|  | View respondents | List view
View survey response
Preview survey
Download survey report
Library Category
Add library category
List view
Edit library category
Back
Search
Surveyor List
Survey list
|  | Syncronized | View survey response
Not Syncronized
Submit all response
Sync survey list
Sync survey respondents
Add respone
Terms policy
Save survey response

## Survey App Effort
EPIC | User Story | Task | Sub Task | Web Forms | PM | BA | Architect | Tech Lead | Dev1 | Dev2 | Test Lead | Test Engineer | DBA | DB Developer | UX | UI | Cloud Architect | DevOps Engineer
| Login features |  |  | Authentication & Authorization | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 2 | 2
|  | Login |  | Send Notification
|  | Forgot password |  | Windows Schedular
|  | Remember Me |  | Users
|  | Logout |  | Add
|  | Authorization |  | Manage
| Side Pane |  |  | Bulk Add | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2
|  | Account settings |  | User Assignment
|  |  | User details | Department
|  |  | Change password | Add
|  | Menu |  | Customer Group
Users |  |  |  | Add
| Manage users |  |  | Bulk Add | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 3 | 3
Search
Reset
Export
List view
Add user
|  | Add multiple user |  |  | 3 | 3 | 3 | 4 | 5 | 5 | 2 | 4 | 1 | 2 | 4 | 4
Download user template
Download user assignment template
Upload file
Edit user
Cancel & Back
User assignment
Department
|  | Search |  |  | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 2
Export
List view
Add Department
Edit Department
| Customer group |  |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
Search
Export
List view
Add customer group
Add multiple customer group
Download template
Upload file
|  |  | Cancel & Back | Territory
|  | Edit customer group |  | Add
| Territory |  |  |  | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 2
Search
Export
List view
|  | Add Territory |  | Commericial unit
|  | Edit Territory |  | Add
| Commericial unit |  |  | Bulk Add | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
Search
Export
List view
Add commercial unit
Add multiple commercial unit
Download template
|  |  | Upload file | Region
|  |  | Cancel & Back | Add
|  | Edit commercial unit |  | Bulk Add
| Region |  |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
Search
Export
List view
Add region
Add multiple region
Download region template
Download commericial unit template
|  |  | Download territory data template | Sales location
|  |  | Upload file | Add
|  |  | Cancel & Back | Bulk Add
Edit commercial unit
Sales location
|  | Search |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
Export
List view
Add sales location
Add multiple sales location
Download sales location template
|  |  | Download region template | Survey List View
|  |  | Upload file | Add
|  |  | Cancel & Back | Bulk Add
|  | Edit sales location |  | Dash Board
Surveys
| Survey List View |  |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
Dashboard
Total Survey
Published
Draft
Expired
Closed
Actions
Duplicate Report
|  |  | Download Export Report | Dash Board
|  |  | Close Survey | Add
|  |  | View Respondents | Bulk Add
|  |  | Preview Survey | Delete
Surveys |  |  |  | Display | 7 | 7 | 7 | 10 | 15 | 15 | 8 | 15 | 8 | 15 | 10 | 12
| Dash Board & List View |  |  | Move Section
|  | Search |  | Change Question
|  | Create Survey |  | Add Section
Add section
Add Question
Question display
Select type of question
Edit question
Delete question
Change question type
|  |  | Move to section | Select
|  |  | Question display | Delete
|  | Edit Survey |  | Move Section
|  | Add section |  | Change Question
|  | Add Question |  | Duplication
|  |  | Select type of question | Close
|  |  | Edit question | View Responses
Delete question
Change question type
Move to section
Duplicate survey
Close survey
|  | View respondents |  | List Category
|  |  | List view | Add
|  |  | View survey response | Edit
Preview survey
Download survey report
| Library Category |  |  |  | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 2
Add library category
List view
Edit library category
Back
Search
Mobile App |  |  |  | Surveyor List
| Authentication |  |  | Syncronized | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
|  | Login |  | Not syncronized
|  | Forgot Password |  | Sync List
|  | Logout |  | Add Response
| Surveyor List |  |  | Survey Reponse | 4 | 4 | 4 | 6 | 8 | 8 | 3 | 4 | 2 | 4 | 5 | 7
Survey list
Syncronized
View survey response
Not Syncronized
Submit all response
|  | Sync survey list |  | Email Functionality
|  | Sync survey respondents |  | Windows Schedular
Add respone
Terms policy
Save survey response
| Email Functionality |  |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
| Windows Schedular |  |  |  | 3 | 3 | 4 | 4 | 8 | 8 | 4 | 8 | 2 | 5 | 4 | 5
5 | 16 | 82 | 44 | 54 | 40 | 40 | 40 | 57 | 90 | 90 | 41 | 67 | 26 | 50 | 49 | 62

## Survey Mobile App (hidden)
EPIC | User Story | Task | Sub Task | PM | BA | Architect | Tech Lead | Dev1 | Dev2 | Test Lead | Test Engineer | DBA | DB Developer | UX | UI | Cloud Architect | DevOps Engineer
| Authentication |  |  | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 3
Login
Forgot Password
Logout
| Surveyor List |  |  | 4 | 4 | 4 | 6 | 8 | 8 | 3 | 4 | 2 | 4 | 5 | 7
Survey list
Syncronized
View survey response
Not Syncronized
Submit all response
Sync survey list
Sync survey respondents
Add respone
Terms policy
Save survey response
|  |  |  | 6 | 6 | 6 | 9 | 13 | 13 | 5 | 7 | 3 | 6 | 7 | 10

## JDs
SDM
Project Manager | Total Experience:10-12 Years Agile, Scrum, ITIL & PMP certiffied Technical ManagerReview existing solutions, identify opportunities for continuous improvements, and perform enhancements to systems. Understand .NET & Cloud systems architecture with high customization and complex business process and recommend/implement scalable solutions. Manage systems integrations to/from the application and assist in data transfers. Work with infrastructure team to ensure the public cloud environment is tuned to optimum efficiency. Manage SLAs and guide the team to triage, identify and recommend technical solutions for fixing issues and enhancements. Collaborate and work with business and cross-functional teams to identify & implement effective solutions that automates and optimizes system performance and business processes, including scaling cloud-native applications.
UX | Total Experience:5-6 Years Strong proficiency in HTML, CSS, JavaScript, and ASP.NET Razor syntax, Experience with front-end frameworks/libraries (e.g., jQuery, Bootstrap), Familiarity with responsive web design and mobile-first development, Knowledge of ASP.NET MVC and ASP.NET Web API, Understanding of browser developer tools for debugging, Experience with Visual Studio or other ASP.NET development tools, Excellent problem-solving and communication skills, Attention to detail and a strong eye for design, Ability to work both independently and collaboratively in a team environment, Portfolio of previous web development projects, especially those involving ASP.NET
UI | Total Experience:5-6 Years Collaborate with back-end developers to seamlessly integrate user interfaces with ASP.NET applications, Create visually appealing and responsive web pages using HTML, CSS, JavaScript, and ASP.NET Razor syntax, UI/UX Implementation: Transform design concepts into interactive web elements, maintaining design consistency and optimizing user experience, Develop components to display and manipulate data retrieved from ASP.NET APIs or databases, Client-Side Scripting: Write scripts to enhance user interactivity and validate user input, Cross-Browser Compatibility: Ensure web applications function correctly across various browsers and devices, Performance Optimization: Optimize web pages for speed and efficiency to minimize load times, Responsive Design: Implement layouts that adapt to different screen s and resolutions. Code Quality: Write clean, well-documented, and maintainable code following ASP.NET and industry best practices
BA | Total Experience:6-8 Years Proficient in Food and Bevarages industry, retail, wholesale, taxation, Finance and credit applications Analyzing data, creating FSD, BRD, identifying business processes, and translating business requirements into technical specifications. He/She should communicate with stakeholders to ensure that the business needs are met.
Pre-Sales Solution Architect | Total Experience:14-18 Years Pre-Sales Soluiton Achitect having relevant Microsoft Azure architecture, design & delivery experience Consulting experience with large-scale implementations on Microsoft Azure Experience in Azure Infra, Networks, Storage, Apps and Azure DevOps Experience in Creating solutions, presenting and articulating winning prepositions for Microsoft Azure Well versed with cloud architecture styles and design patterns Experience in developing cloud migration approaches, defining migration roadmaps and providing estimates Experience with Azure Resource Manager, Resource Groups, Virtual Networks, Azure Virtual Machines, Azure Blob Storage, PowerShell DSC, Azure Automation, Azure Active Directory, and Azure Site Recovery Experience in developing and deploying Cloud Native Applications using Azure PaaS Capabilities (App Services Plans, Key Vault, SQL Azure DB, Azure Functions, Containers, AKS, Logic Apps, Service Bus, Event Grid, API Management) Experience in Enterprise Integration Technologies such as BizTalk, Azure API Management, Logic Apps, Service Bus Demonstrates strong analytical and technical problem-solving skills
Azure Cloud Architecture | Total Experience:10-12 Years Primary Skills: az305, az104 Azure Solution Architect. Azure- Infra, Security, Mornitoring, Data & Storage, Networking, Compute, Analytics, DevSecOps, Web & Mobile, Fabric, ASP.Net Core, PaaS, IaaS, FaaS, SaaS Secondary: Knowlodege on application migration and modernization, Best Practices, Azure Cost Factors, DR, design, build, implement, and manage Azure systems, while ensuring security, scalability, and dependability.
Azue DevOps Engineer | Total Experience: 5-7 Years. AZ400 Certfied DevOps Engineer. Primary Skills:Proficiency in Azure DevOps or GitHub, continuous integration, continuous delivery, pipelines, and Git version control, Azure Containers Seconary Skills: , AKS, PowerShell and Azure CLI, App Services, Good Knowledge on Azure networking, virtual networks, firewalls, load balancers, and VPNs.
Azure .Net Tech Lad | Total Experience: 7-9 Years Primary Skills: Azure Schedular, Azure Logic App, Azure App Service Plan and App Services, . Net Core, . Net Framework, C#/.Net, ASP.NET, SQL, JavaScript, HTML5, CSS Secondary Skills: DB Development SQL Server, Azure Storage and MS Defender, Azure Funtions, github Good to have: SSO integration, PDF generation using ASP.NET Web application, Azure networking, virtual networks, firewalls, load balancers, and VPNs.
Azure .Net Developer | Total Experience: 4-5 Years Primary Skills: Azure Schedular, Azure Logic App, Azure App Service Plan and App Services, . Net Core, . Net Framework, C#/.Net, ASP.NET, SQL, JavaScript, HTML5, CSS Secondary Skills: DB Development SQL Server, Azure Storage and MS Defender, Azure Funtions, github Good to have: SSO integration, PDF generation using ASP.NET Web application, Azure networking, virtual networks, firewalls, load balancers, and VPNs.
Test Lead | Total Yrs of experience: 7-9 years of overall testing experience with a minimum 4 years experience with APIs, mobile and web app testing, Experience of 4 years or higher in Food&Bevarages and Financial services Test planning: Developing test plans, including the objectives, scope, test levels, test techniques, and resources required Test strategy development: Devising a comprehensive test strategy that outlines the overall approach to testing the software application, Test case review: Reviewing test cases, Overseeing test execution: Coordinating and overseeing the actual testing activities, Defect management: Managing defects, Reporting: Writing reports, Team management: Allocating tasks to team members, monitoring their progress, and providing guidance and support whenever required
Web App Tester | Total Yrs of experience: 4-5 years of overall testing experience with a minimum 6 years experience with APIs, mobile and web app testing, Strong ability to execute functional tests on mobile app with Usability / user experience requirements Experience of 4 years or higher in Food&Bevarages and Financial services
Database Admin | Total Yrs of experience: 7-9 Responsible for a database's performance, integrity, and security Maintain databases with high-availability solutions, replication, backup, restore, encryption, and disaster recovery solutions. Strong database migration experience, Expertise and experience monitoring Azure workspaces, VM's, VM drives, Memory etc.s Monitor system's health and performance, Ensure high levels of performance, availability, sustainability and security Analyze, solve, and correct issues in real time, Provide suggestions for solutions, Refine and automate regular processes, track issues, and document changes, Assist developers with query tuning and schema refinement, Provide 24x7 support for critical production systems, Perform scheduled maintenance and support release deployment activities after hours
SQL Developer | Total Yrs of experience: 7-9 Develop Database components using Azure SQL Database SQL Server and related technologies and implementing best engineering designs. Develop business applications on the cloud (Microsoft Azure) implementing Ecommerce, Marketplace and Operational components enabling digital transformation for healthcare.
Mobile Developer | Deep knowledge of Android, iOS mobile development, Familiarity with RESTful APIs and mobile libraries for networking, Familiarity with the JSON format, Experience with profiling and debugging mobile applications, Strong knowledge of architectural patterns like MVP, MVC, MVVM, and Clean Architecture and the ability to choose the best solution for the app, Git, Familiarity with push notifications, mobile app design guidelines on each platform, C#..
Pre-Sales Solution Architect

## Working-IND_30
FTE | Role | Experience Level | Duration | Manhours | Monthly Cost/ Pay Rate | Leave Encashment Cost | Public Holiday Cost | Monthly Gratuity Cost | Monthly PF Admin Charges | Monthly Medical Cost | Monthly Payroll Cost | Monthly BGV cost | Shift Allowance | Monthly Cost | Laptop Copsts | Total Monthly Cost | Marup% | Markup | Monthly BR | Project Cost | Project Revenue | GP | GPM
0.66667 | Project Manager | 10+ Years | 9 | 1044 | 266666.6667 | 14303.9591 | 0 | 12826.6667 | 1994.6667 | 333.3333 | 50 | 388.8889 | 0 | 296564.1814 | 2222.2222 | 298786.4036 | 43% | 127522.598 | 426309.0016 | 1792718.4215 | 2557854.0093 | 765135.5879 | 29.91%
1 | Senior BA | 6 Years | 9 | 1566 | 200000 | 10727.9693 | 0 | 9620 | 1496 | 333.3333 | 50 | 388.8889 | 0 | 222616.1916 | 2222.2222 | 224838.4138 | 43% | 95724.9624 | 320563.3762 | 2023545.7241 | 2885070.3855 | 861524.6614 | 29.86%
1 | Presales Solution Architect | 10+ Years | 2 | 348 | 333333.3333 | 17879.9489 |  | 16033.3333 | 2493.3333 | 1500 | 50 | 1750 | 0 | 373039.9489 | 2222.2222 | 375262.1711 | 43% | 160407.178 | 535669.3492 | 750524.3423 | 1071338.6983 | 320814.3561 | 29.95%
1 | Senior Delivery Manager | 10+ Years | 2 | 348 | 150000 | 8045.977 |  | 7215 | 1122 | 1500 | 50 | 1750 | 0 | 169682.977 | 2222.2222 | 171905.1992 | 43% | 72963.6801 | 244868.8793 | 343810.3985 | 489737.7587 | 145927.3602 | 29.8%
0.66667 | Technical Architect | 12 years | 9 | 1044 | 375000 | 20114.9425 | 0 | 18037.5 | 2805 | 333.3333 | 50 | 388.8889 | 0 | 416729.6648 | 2222.2222 | 418951.887 | 43% | 179193.7558 | 598145.6428 | 2513711.3218 | 3588873.8569 | 1075162.5351 | 29.96%
1 | .Net Technical Lead | 8+ Years | 8 | 1392 | 266666.6667 | 14303.9591 | 0 | 12826.6667 | 1994.6667 | 375 | 50 | 437.5 | 0 | 296654.4591 | 2222.2222 | 298876.6814 | 43% | 127561.4174 | 426438.0988 | 2391013.4508 | 3411504.7902 | 1020491.3394 | 29.91%
1 | Front End Technical Lead | 10+ Years | 8 | 1392 | 266666.6667 | 14303.9591 | 0 | 12826.6667 | 1994.6667 | 375 | 50 | 437.5 | 0 | 296654.4591 | 2222.2222 | 298876.6814 | 43% | 127561.4174 | 426438.0988 | 2391013.4508 | 3411504.7902 | 1020491.3394 | 29.91%
2 | Senior .Net Developer | 5+ Years | 8.5 | 2958 | 183333.3333 | 9833.9719 | 0 | 8818.3333 | 1371.3333 | 352.9412 | 50 | 411.7647 | 0 | 204171.6778 | 2222.2222 | 206393.9 | 43% | 87793.8214 | 294187.7215 | 3508696.3001 | 5001191.2647 | 1492494.9646 | 29.84%
1 | Junior .Net Developer | 3+ Years | 9 | 1566 | 150000 | 8045.977 | 0 | 7215 | 1122 | 333.3333 | 50 | 388.8889 | 0 | 167155.1992 | 2222.2222 | 169377.4215 | 43% | 71876.7357 | 241254.1571 | 1524396.7931 | 2171287.4141 | 646890.621 | 29.79%
0.25 | Database Admin / Architect | 10+ years | 7 | 304.5 | 300000 | 16091.954 | 0 | 14430 | 2244 | 428.5714 | 50 | 500 | 0 | 333744.5255 | 2222.2222 | 335966.7477 | 43% | 143510.1459 | 479476.8936 | 587941.8084 | 839084.5638 | 251142.7554 | 29.93%
1 | SQL Developer | 3+ Years | 7 | 1218 | 83333.3333 | 4469.9872 | 0 | 4008.3333 | 623.3333 | 428.5714 | 50 | 500 | 0 | 93413.5587 | 2222.2222 | 95635.7809 | 43% | 40167.8302 | 135803.6111 | 669450.4662 | 950625.2777 | 281174.8116 | 29.58%
1 | Senior SQL Developer | 5+ Years | 7 | 1218 | 166666.6667 | 8939.9745 | 0 | 8016.6667 | 1246.6667 | 428.5714 | 50 | 500 | 0 | 185848.5459 | 2222.2222 | 188070.7681 | 43% | 79914.8747 | 267985.6428 | 1316495.3768 | 1875899.4999 | 559404.1231 | 29.82%
1 | Senior UX Designer | 6+ years | 8 | 1392 | 208333.3333 | 11174.9681 | 0 | 10020.8333 | 1558.3333 | 375 | 50 | 437.5 | 0 | 231949.9681 | 2222.2222 | 234172.1903 | 43% | 99738.4863 | 333910.6766 | 1873377.5223 | 2671285.4125 | 797907.8902 | 29.87%
1 | Front End Developer | 3+ Years | 7 | 1218 | 175000 | 9386.9732 | 0 | 8417.5 | 1309 | 428.5714 | 50 | 500 | 0 | 195092.0446 | 2222.2222 | 197314.2668 | 43% | 83889.5792 | 281203.846 | 1381199.8678 | 1968426.9221 | 587227.0543 | 29.83%
2 | Senior Front end Developer | 5+ Years | 8 | 2784 | 225000 | 12068.9655 | 0 | 10822.5 | 1683 | 375 | 50 | 437.5 | 0 | 250436.9655 | 2222.2222 | 252659.1877 | 43% | 107687.8952 | 360347.0829 | 4042547.0038 | 5765553.3266 | 1723006.3228 | 29.88%
1 | Senior UI Designer | 6+ years | 8 | 1392 | 225000 | 12068.9655 | 0 | 10822.5 | 1683 | 375 | 50 | 437.5 | 0 | 250436.9655 | 2222.2222 | 252659.1877 | 43% | 107687.8952 | 360347.0829 | 2021273.5019 | 2882776.6633 | 861503.1614 | 29.88%
1 | Azure Cloud Architect | 10+ Years | 3 | 522 | 316666.6667 | 16985.9515 | 0 | 15231.6667 | 2368.6667 | 1000 | 50 | 1166.6667 | 0 | 353469.6181 | 2222.2222 | 355691.8404 | 43% | 151991.9358 | 507683.7762 | 1067075.5211 | 1523051.3285 | 455975.8074 | 29.94%
1 | Senior Devops Engineer | 6+ Years | 6 | 1044 | 208333.3333 | 11174.9681 | 0 | 10020.8333 | 1558.3333 | 500 | 50 | 583.3333 | 0 | 232220.8014 | 2222.2222 | 234443.0236 | 43% | 99854.9446 | 334297.9682 | 1406658.1418 | 2005787.8094 | 599129.6676 | 29.87%
1 | Test Lead | 8+ Years | 7 | 1218 | 225000 | 12068.9655 | 0 | 10822.5 | 1683 | 428.5714 | 50 | 500 | 0 | 250553.0369 | 2222.2222 | 252775.2592 | 43% | 107737.8059 | 360513.0651 | 1769426.8142 | 2523591.4554 | 754164.6412 | 29.88%
1 | Jr Test Engineer | 1-3 Years | 7 | 1218 | 91666.6667 | 4916.986 | 0 | 4409.1667 | 685.6667 | 428.5714 | 50 | 500 | 0 | 102657.0574 | 2222.2222 | 104879.2796 | 43% | 44142.5347 | 149021.8143 | 734154.9572 | 1043152.6999 | 308997.7427 | 29.62%
1 | Senior Test Engineer | 5+ Years | 7 | 1218 | 166666.6667 | 8939.9745 | 0 | 8016.6667 | 1246.6667 | 428.5714 | 50 | 500 | 0 | 185848.5459 | 2222.2222 | 188070.7681 | 43% | 79914.8747 | 267985.6428 | 1316495.3768 | 1875899.4999 | 559404.1231 | 29.82%
1 | Senior Mobile Developer | 6+ years | 6 | 1044 | 166666.6667 | 8939.9745 | 0 | 8016.6667 | 1246.6667 | 500 | 50 | 583.3333 | 0 | 186003.3078 | 2222.2222 | 188225.53 | 43% | 79981.4223 | 268206.9524 | 1129353.1801 | 1609241.7142 | 479888.5341 | 29.82%
22.5833 |  |  |  |  | 4750000 | 254789.272 | 0 | 228475 | 35530 | 11561.2745 | 1100 | 13488.1536 | 0 | 5294943.7001 | 48888.8889 | 5343832.589 |  | 2276825.7911 | 7620658.3801 | 36554879.7414 | 52122739.1413 | 15567859.3999 | 29.87%
Non People Cost
[19 empty] | Travel | 0
POC Cost
[19 empty] | Total Cost | 36554879.7414 | 52122739.1413 | 15567859.3999
[21 empty] | INR Currency | PHP Currency
[20 empty] | Revenue | 52122739.1413 | 35218066.9874
[20 empty] | Cost | 36554879.7414 | 24699243.0685
[20 empty] | GP | 15567859.3999 | 10518823.9189
[20 empty] | GPM for the Project | 29.87% | 29.87%

## Login Details (hidden)
CWT | Dev : https://cocacolaph-dev.outsystemsenterprise.com/CWT | c-chris.lugue@coca-cola.com.ph | Cokewilkins1234* | Admin
Digitizing CAF | https://cocacolaph-tst.outsystemsenterprise.com/CAF_Internal | CAF_Admin@cocacola.com | P@ssw0rd123 | Admin
| https://cocacolaph-tst.outsystemsenterprise.com/CustomerManagement/ |  |  | Customer
Site Admin
Dev : https://cocacolaph-dev.outsystemsenterprise.com/CWT
Uname - c-sanjay.mahadevanayaka@coca-cola.com.ph
Password - !Coke@1044407
TaxLead
Uname - c-chethan.chandrashekhar@coca-cola.com.ph
Pass - G0wd@Ch3t#@n7
Pausechallenge833
https://www.youtube.com/watch?v=HfyAxPvBwIE
https://collaberadigitaltechnology.sharepoint.com/sites/CES-CCBPI_Transition/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=cecRAP&ovuser=3d089d0c%2Dc75a%2D4ec9%2D8abc%2D782fc5b42299%2Cc%2Daparupa%2Esengupta%40coca%2Dcola%2Ecom%2Eph&OR=Teams%2DHL&CT=1711609148560&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIxNDE1LzI0MDIyOTIwNjAyIiwiSGFzRmVkZXJhdGVkVXNlciI6ZmFsc2V9&cid=a62b8270%2D6bfa%2D47d5%2Db3a2%2D7cf5a2fb0e19&FolderCTID=0x012000991DD73A1A074D469F0B54148D6EE395&id=%2Fsites%2FCES%2DCCBPI%5FTransition%2FShared%20Documents%2FOut%20System%20Migration%2FInternal%20Document%20Sharing&viewid=eb4f162e%2Dc5b9%2D4a7c%2Db58e%2D7e07228ec85b
Coke Survey App is used to conduct surveys, to manage survey questions and to manage survey results.
Site Admin
CWT | Dev : https://cocacolaph-dev.outsystemsenterprise.com/CWT | c-chris.lugue@coca-cola.com.ph | Cokewilkins1234* | Admin
Digitizing CAF | https://cocacolaph-tst.outsystemsenterprise.com/CAF_Internal | CAF_Admin@cocacola.com | P@ssw0rd123 | Admin
https://cocacolaph-tst.outsystemsenterprise.com/CustomerManagement/ |  | Customer
Dev : https://cocacolaph-dev.outsystemsenterprise.com/CWT
Uname - c-sanjay.mahadevanayaka@coca-cola.com.ph
Password - !Coke@1044407
TaxLead
Uname - c-chethan.chandrashekhar@coca-cola.com.ph
Pass - G0wd@Ch3t#@n7
Admin : Configuration
https://cocacolaph-dev.outsystemsenterprise.com/CAF_Common/Login
User name : CAF_Admin@cocacola.com
Password : P@ssw0rd123
Approver Email ID: reynaldo.abellera@coca-cola.com.ph/jayson.catacutan@dbresults.com.hk
Admin Customer confi:
https://cocacolaph-dev.outsystemsenterprise.com/CustomerManagement/Login
User name : CAF_Admin@cocacola.com
Password : P@ssw0rd123
Customer Login :
https://cocacolaph-dev.outsystemsenterprise.com/CAF_Common/CustomerLogin
User Name: Approver/Customer mail - 502147751

## Survey Details (hidden)
|  |  |  | PM | BA | Architect | Tech Lead | Dev1 | Dev2 | Test Lead | Test Engineer | DBA | DB Developer | UX | UI | Cloud Architect | DevOps Engineer
Surveys
| Dash Board & List View |  |  | 2 | 3 | 3 | 3 | 5 | 5 | 3 | 5 | 1 | 3 | 2 | 3
Search
Create Survey
Add section
|  | Add Question |  | 4 | 4 | 4 | 5 | 8 | 8 | 3 | 6 | 5 | 8 | 6 | 8
Question display
Select type of question
Edit question
Delete question
Change question type
Move to section
Question display
|  | Edit Survey |  | 4 | 4 | 4 | 5 | 8 | 8 | 3 | 6 | 5 | 8 | 6 | 8
Add section
|  |  | Add Question | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 3 | 2 | 2
Select type of question
Edit question
Delete question
Change question type
Move to section
|  | Duplicate survey |  | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1
|  |  | Pubish Survey | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1
Close survey
|  | View respondents |  | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 3 | 2 | 2
List view
View survey response
|  | Preview survey |  | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1
Download survey report
|  |  |  | 15 | 16 | 16 | 18 | 34 | 34 | 16 | 30 | 16 | 28 | 21 | 26 | 0 | 0

## DI Audit logs Details (hidden)
Audit Logs |  |  | 4 | 4 | 4 | 8 | 12 | 12 | 8 | 12 | 4 | 8 | 8 | 8
| Print Log | Filter Search | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 2
Export Report
List View
| Approver Log | Filter Search | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 2
Export Report
List View
| Email Log | Filter Search | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 2
Export Report
List View
| Invoice Log | Filter Search | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 2
Export Report
List View